## WBS
Work Breakdown Structure |  |  | Green Grand River Mobility
| Project Start | 2024-01-03
Level | WBS | Task Description | Notes
1 | 1 | PLANNING PHASE
2 | 1.1 | Infrastructure Upgrade | Upgrade infrastructure for efficiency
3 | 1.1.1 | Infrastructure Assessment | Assessment of the current infrastructures
3 | 1.1.2 | Design and Specification Development | Product features and requirement design
2 | 1.2 | Procurement plan | Details of the procurement process
3 | 1.2.1 | Vendor Identification and selection | Vendor selection process
3 | 1.2.2 | Procurement Strategy and planning | Procurement approaches and strategies
2 | 1.3 | Routes Optimization | Routes Improvement process
3 | 1.3.1 | Data collection and Analysis | Relevant data on demand, road conditions and traffic
3 | 1.3.2 | Routes Update | Implementation of the new routes
2 | 1.4 | Fare Structure Analysis | Fare structure evaluation
3 | 1.4.1 | Analysis of Current Fare Structure | Current fare structure analysis
3 | 1.4.2 | Student fare reduction proposal | A proposal to reduced student fares
3 | 1.4.3 | Financial Impact assessment | The financial impact of the reduced fare proposal and recommendation
3 | 1.4.4 | Communications and Report | Communicating the new development to relevant stakeholders
3 | 1.4.5 | Fare structure Implementation | Implementing the new fare structure
1 | 2 | EXECUTION PHASE
2 | 2.1 | Workforce Expansion | Increasing the GRT workforce
3 | 2.1.1 | Recruitment Strategies | Effective staff recuritment strategies
3 | 2.1.2 | Hiring Process | Hiring and onboarding of new employees
2 | 2.2 | Promotion and Awareness | Rasing awareness about the project and new development to the transit system
3 | 2.2.1 | Promotional videos | Details of creation process of the promotional videos
2 | 2.3 | Construction Plan | Construction of the infrastructures
3 | 2.3.1 | Site assessment | Site survey
3 | 2.3.2 | Blueprint development and execution | Details of the constructing process
3 | 2.3.3 | Quality Control and Inspections | Compliance with project requirements and regulatory body
2 | 2.4 | Communications | The project means of reaching out to relevant stakeholders
3 | 2.4.1 | Press release | Announcing the start of the project
3 | 2.4.2 | Social media | Up to dates information about the project phases
3 | 2.4.3 | Media Outreach | Engaging media for project visibility
3 | 2.4.4 | Website Updates | Updating project information and promoting online presence
3 | 2.4.5 | Posting Flyers at Bus Stops and Terminals | Publicity and awareness
1 | 3 | MONITORING AND CONTROLLING PHASE
2 | 3.1 | Performance Monitoring System | System for tracking project success
3 | 3.1.1 | User Satisfaction Feedback System | Feedback system to know commuters satisfaction with our services
3 | 3.1.2 | Key Performance Indicators (KPIS) System | Success criteria
2 | 3.2 | SDG Alignment Assessment | Evaluating SDG alignment for project
3 | 3.2.1 | Data Collection and Analysis | Collecting and analyzing relevant data on carbon footprint in the region
3 | 3.2.2 | Impact Assessment | Assessing project's environmental impact
3 | 3.2.3 | Final SDG Alignment Assessment Report | Concluding SDG alignment assessment report
1 | 4 | CLOSING PHASE
2 | 4.1 | Project Closure and Evaluation | Concluding project
3 | 4.1.1 | Project Closeout | Closing project and handing over operations
3 | 4.1.2 | Lessons Learned Documentation | Recording valuable project insights
◄ Add new rows ABOVE this one.